## history (hidden)
개정이력
NO | 버전 | 변경일 | 변경사유 | 변경내용 | 작성자 | 승인일 | 승인자
1 | 1 | 2016-06-15 | 신규생성 |  | 오이택

## WBS
* brand Korea e-Commerce WBS [Ver.20180401180000] | [11 empty] | *기준일자 : | 2022-11-24 | 계획진척 : | 69.8% | 실제진척 : | 52.54% | SPI : | 0.75285 | (경고)
No | WBS Code | Dep | 작업명 |  |  |  | 계획 | [5 empty] | 진행도 |  |  | 업무 구성비 | 구성진행비율 |  |  |  | 비고(산출물)
[7 empty] | 기간 | 시작일 | 종료일 | 담당자 | 담당자 | 진척율 | 시작일 | 종료일 | 진척율 |  | 계획 | 실적 | 잔여일 | 차
0 | Project | 0 | 수포자들을 위한 게임 |  |  |  | 53일 | 2022-10-03 | 2022-12-14 | breeze | 정성오 | 69.8% | 2022-10-03 |  | 52.54% | 100% | 69.79% | 52.54% | 15 | -17.25% |  | 11/23 (주간회의 - 이슈)
1 | Project 0 | 1 |  | Milestone |  |  | 기간: #REF!; 시작일: #REF!; 종료일: #REF! | [6 empty] | *기준일자 : | 2022-11-24 | 계획진척 : | 69.8% | 실제진척 : | 52.54% | SPI : | 0.75285 | (경고)
2 | Project 1 | 2 |  |  | 1) 구축준비 |  | #VALUE! | 2022-10-03 | 2022-12-12 |  |  | 75.75% | 2022-10-03 |  | 60% | 30% | 22.73% | 18% | 18 | -15.75%
3 | Project 2 | 2 |  |  | 2) 기본정보 |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | Project 3 | 2 |  |  | 3) 외부 연동 계정 생성 |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
3 | Project 4 | 2 |  |  | 4) 연동정보 설정 |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | Project 5 | 2 |  |  | 5) 서비스 구조 설정 |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! |  |  | #REF! | 0% | #REF!
3 | Project 6 | 2 |  |  | 6) 교육 |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | Project 7 | 2 |  |  | 7) Contents등록 |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | Project 8 | 2 |  |  | 8) 카드심사 |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | Project 9 | 2 |  |  | 9) 추가개발 |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | Project 10 | 2 |  |  | 10) 테스트 |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | Project 11 | 2 |  |  | 11) 서비스 오픈 |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1 | Project 1 | 1 |  | 게임 부분 |  |  | 51일 | 2022-10-03 | 2022-12-12 | breeze | 정성오 | 75.75% | 2022-10-03 |  | 60% | 30% | 22.73% | 18% | 13 | -15.75% |  |  | 1) 본인인증 한국모바일인증에서 제공해 주는 창을 사용해도 될지?
2 | Project 1.1 | 2 |  |  | 구조 설계 |  | 51일 | 2022-10-03 | 2022-12-12 | breeze | 정성오 | 75.75% | 2022-10-03 |  | 60% | 100% | 75.75% | 60% | 13 | -15.75%
3 | Project 1.1.1 | 3 |  |  |  | 기믹 설계 | 40일 | 2022-10-03 | 2022-11-27 | breeze | 정성오 | 97.5% | 2022-10-03 |  | 90% | 20% | 19.5% | 18% | 2 | -7.5%
4 | Project 1.1.2 | 3 |  |  |  | ui 작업 | 40일 | 2022-10-03 | 2022-11-27 | 브랜드 | 정성오 | 97.5% | 2022-10-03 |  | 70% | 30% | 29.25% | 21% | 2 | -27.5%
5 | Project 1.1.3 | 3 |  |  |  | 그래픽 작업 | 10일 | 2022-11-14 | 2022-11-27 | 브랜드 | 정성오 | 90% | 2022-11-18 |  | 70% | 30% | 27% | 21% | 2 | -20%
6 | Project 1.1.4 | 3 |  |  |  | 음향 작업 | 11일 | 2022-11-28 | 2022-12-12 | 브랜드 | 정성오 | 0% |  |  | 0% | 20% | 0% | 0% | 13 | 0%
7 | Project 2 | 1 |  | 기능 |  |  | 51일 | 2022-10-03 | 2022-12-12 | breeze | 성한솔,김종환 | 78.45% | 2022-10-03 |  | 57.57% | 60% | 47.07% | 34.54% | 13 | -20.87%
8 | Project 2.1 | 2 |  |  | 그래픽 |  | 31일 | 2022-10-03 | 2022-11-14 | breeze | 성한솔 | 100% | 2022-10-03 |  | 70% | 30% | 30% | 21% | 0 | -30%
9 | Project 2.2 | 2 |  |  | 세부 기능 |  | 51일 | 2022-10-03 | 2022-12-12 | breeze | 성한솔, 김종환 | 69.21% | 2022-10-03 |  | 52.25% | 70% | 48.45% | 36.57% | 13 | -16.96%
10 | Project 2.2.1 | 3 |  |  |  | 홈 화면 | 25일 | 2022-10-03 | 2022-11-06 | breeze | 김종환 | 100% | 2022-10-03 |  | 65% | 25% | 25% | 16.25% | 0 | -35%
11 | Project 2.2.2 | 3 |  |  |  | 메뉴 | 5일 | 2022-11-07 | 2022-11-13 | breeze | 김종환, 성한솔 | 100% | 2022/10/09(목) |  | 80% | 20% | 20% | 16% | 0 | -20%
12 | Project 2.2.3 | 3 |  |  |  | 점수 기록 | 10일 | 2022-11-14 | 2022-11-27 | breeze | 김종환 | 90% |  |  | 0% | 15% | 13.5% | 0% | 2 | -90%
13 | Project 2.2.4 | 3 |  |  |  | 오답노트 | 11일 | 2022-11-28 | 2022-12-12 | breeze | 김종환 | 0% |  |  | 0% | 15% | 0% | 0% | 13 | 0%
14 | Project 2.2.5 | 3 |  |  |  | 추천 | 21일 | 2022-11-14 | 2022-12-12 | breeze | 성한솔 | 42.86% |  |  | 80% | 25% | 10.71% | 20% | 13 | 37.14%
15 | Project 4 | 1 |  | 테스트 |  |  | 7일 | 2022-12-06 | 2022-12-14 | breeze | 전원 | 0% |  |  | 0% | 10% | 0% | 0% | 15 | 0%
16 | Project 4.1 | 2 |  |  | 테스트 및 오류 수정 |  | 2일 | 2022-12-13 | 2022-12-14 | 전체 | 전원 | 0% |  |  | 0% | 50% | 0% | 0% | 15 | 0%
17 | Project 4.2 | 2 |  |  | 최종 보고서 작성 기간 |  | 7일 | 2022-12-06 | 2022-12-14 | 전체 | 전원 | 0% |  |  | 0% | 50% | 0% | 0% | 15 | 0%
Formulas:
잔여일 = IF([종료일]-P2<=0,0,CONCATENATE(NETWORKDAYS(P2,[종료일],holiday!B4:B39)))
잔여일 = IF(COUNTBLANK([시작일]:[종료일])>0,0,IF([종료일]-P2<=0,0,NETWORKDAYS(P2,[종료일],holiday!B4:B39)))

## holiday
공휴일
Date | Remarks
2018-01-01 | 신정
2018-02-15 | 설연휴
2018-02-16 | 설연휴
2018-03-01 | 삼일절
2018-05-07 | 대체휴일
2018-05-22 | 부처님오신날
2018-06-06 | 현충일
2018-06-13 | 지방선거
2018-08-15 | 광복절
2018-09-24 | 추석
2018-09-25 | 추석
2018-09-26 | 대체휴일
2018-10-03 | 개천절
2018-10-09 | 한글날
2018-12-25 | 성탄절