## history (hidden)
개정이력
NO | 버전 | 변경일 | 변경사유 | 변경내용 | 작성자 | 승인일 | 승인자
1 | 1899-12-31 | 42536 | 신규생성 |  | 오이택

## WBS
* brand Korea e-Commerce WBS [Ver.20180401180000] | [11 empty] | *기준일자 : | 44867 | 계획진척 : | 33.74% | 실제진척 : | 0.2334 | SPI : | 69.17% | (경고)
No | WBS Code | Dep | 작업명 |  |  |  | 계획 | [5 empty] | 진행도 |  |  | 업무 구성비 | 구성진행비율 |  |  |  | 비고(산출물)
[7 empty] | 기간 | 시작일 | 종료일 | 담당자 | 담당자 | 진척율 | 시작일 | 종료일 | 진척율 |  | 계획 | 실적 | 잔여일 | 차
0 | Project | 0 | 수포자들을 위한 게임 |  |  |  | 53일 | 44837 | 44909 | breeze | 정성오 | 33.74% | 4483700% |  | 23.34% | 100% | 33.74% | 23.34% | 31 | -0.10403 |  | 11/23 (주간회의 - 이슈)
1 | Project 0 | 100% |  | Milestone |  |  | 기간: #REF!; 시작일: #REF!; 종료일: #REF! | [6 empty] | *기준일자 : | 44867 | 계획진척 : | 0.33743 | 실제진척 : | 0.2334 | SPI : | 0.69169 | (경고)
2 | Project 1 | 2 |  |  | 1) 구축준비 |  | #VALUE! | 4483700% | 4490700% |  |  | 0.092 | 2022-10-03 |  | 5% | 30% | 0.0276 | 0.015 | 40 | -0.042
3 | Project 2 | 1900-01-01 |  |  | 2) 기본정보 |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | Project 3 | 2 |  |  | 3) 외부 연동 계정 생성 |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
3 | Project 4 | 1900-01-01 |  |  | 4) 연동정보 설정 |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | Project 5 | 2 |  |  | 5) 서비스 구조 설정 |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! |  |  | #REF! | 0 | #REF!
3 | Project 6 | 1900-01-01 |  |  | 6) 교육 |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | Project 7 | 2 |  |  | 7) Contents등록 |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | Project 8 | 1900-01-01 |  |  | 8) 카드심사 |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | Project 9 | 1900-01-01 |  |  | 9) 추가개발 |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | Project 10 | 2 |  |  | 10) 테스트 |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | Project 11 | 1900-01-01 |  |  | 11) 서비스 오픈 |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1 | Project 1 | 1 |  | 게임 부분 |  |  | 51일 | 44837 | 44907 | breeze | 정성오 | 0.092 | 44837 |  | 0.05 | 0.3 | 0.0276 | 0.015 | 2900% | -4.2% |  |  | 1) 본인인증 한국모바일인증에서 제공해 주는 창을 사용해도 될지?
2 | Project 1.1 | 1900-01-01 |  |  | 구조 설계 |  | 51일 | 4483700% | 4490700% | breeze | 정성오 | 0.092 | 44837 |  | 0.05 | 1899-12-31 | 0.092 | 5% | 2900% | -0.042
3 | Project 1.1.1 | 1900-01-02 |  |  |  | 기믹 설계 | 25일 | 44837 | 44871 | breeze | 정성오 | 0.92 | 44837 |  | 0.5 | 0.1 | 9.2% | 5% | 300% | -0.42
4 | Project 1.1.2 | 1900-01-02 |  |  |  | ui 작업 | 5일 | 44872 | 44878 | 브랜드 | 정성오 | 0 |  |  | 0 | 0.2 | 0% | 0% | 800% | 0
5 | Project 1.1.3 | 1900-01-02 |  |  |  | 그래픽 작업 | 10일 | 44879 | 44892 | 브랜드 | 정성오 | 0 |  |  | 0 | 0.2 | 0% | 0% | 1800% | 0
6 | Project 1.1.4 | 1900-01-02 |  |  |  | 음향 작업 | 11일 | 44893 | 44907 | 브랜드 | 정성오 | 0 |  |  | 0 | 0.2 | 0% | 0% | 2900% | 0
7 | Project 2 | 1 |  | 기능 |  |  | 40일 | 44837 | 44892 | breeze | 성한솔,김종환 | 0.51639 | 44837 |  | 0.364 | 0.6 | 0.30983 | 0.2184 | 1800% | -0.15239
8 | Project 2.1 | 1900-01-01 |  |  | 그래픽 |  | 31일 | 4483700% | 4487900% | breeze | 성한솔 | 0.74194 | 44837 |  | 0.5 | 0.2 | 0.14839 | 10% | 900% | -0.24194
9 | Project 2.2 | 1900-01-01 |  |  | 세부 기능 |  | 25일 | 4483700% | 4487100% | breeze | 성한솔, 김종환 | 0.92 | 44837 |  | 0.66 | 0.4 | 0.368 | 26.4% | 300% | -0.26
10 | Project 2.2.1 | 1900-01-02 |  |  |  | 홈 화면 | 25일 | 44837 | 44871 | breeze | 김종환 | 0.92 | 2022-10-03 |  | 0.5 | 1 | 92% | 50% | 300% | -0.42 | 게임과 연동할때 마무리 예정
11 | Project 2.2.2 | 1900-01-02 |  |  |  | 메뉴 | 5일 | 44872 | 44878 | breeze | 김종환 | 0 | 2022/10/09(목) |  | 0.15 | 1 | 0% | 15% | 800% | 0.15 | 홈화면 점수화면 넘기는 구간 작성중
12 | Project 2.2.3 | 1900-01-02 |  |  |  | 점수 기록 | 10일 | 44879 | 44892 | breeze | 김종환 | 0 |  |  | 0.01 | 1 | 0% | 1% | 1800% | 0.01 | 화면만 만든상태
13 | Project 2.2.4 | 1900-01-02 |  |  |  | 오답노트 | 11일 | 44893 | 44907 | breeze | 김종환 | 0 |  |  | 0 | 1 | 0% | 0% | 2900% | 0
14 | Project 2.2.5 | 1900-01-02 |  |  |  | 추천 | 21일 | 44879 | 44907 | breeze | 성한솔 | 0 |  |  | 0 | 1 | 0% | 0% | 2900% | 0
15 | Project 4 | 1899-12-31 |  | 테스트 |  |  | 7일 | 44901 | 44909 | breeze | 전원 | 0 |  |  | 0 | 0.1 | 0 | 0 | 3100% | 0%
16 | Project 4.1 | 2 |  |  | 테스트 및 오류 수정 |  | 2일 | 2022-12-13 | 2022-12-14 | 전체 | 전원 | 0% |  |  | 0 | 0.1 | 0 | 0% | 3100% | 0
17 | Project 4.2 | 2 |  |  | 최종 보고서 작성 기간 |  | 7일 | 2022-12-06 | 2022-12-14 | 전체 | 전원 | 0% |  |  | 0 | 0.1 | 0 | 0% | 3100% | 0
Formulas:
잔여일 = IF([종료일]-P2<=0,0,CONCATENATE(NETWORKDAYS(P2,[종료일],holiday!B4:B39)))
잔여일 = IF(COUNTBLANK([시작일]:[종료일])>0,0,IF([종료일]-P2<=0,0,NETWORKDAYS(P2,[종료일],holiday!B4:B39)))
차 = IF(SUM([구성진행비율]:[실적])>0,([실적]-[구성진행비율])/[업무 구성비],0)
차 = IF(COUNTBLANK([업무 구성비])>0,"",([실적]-[구성진행비율])/[업무 구성비])
Dep = IF(COUNTBLANK([작업명]:I9)<5,IF([작업명]<>"",0,IF(F9<>"",1,IF(G9<>"",2,IF(H9<>"",3,IF(I9<>"",4))))),"")
구성진행비율 = [진척율]*[업무 구성비]

## holiday
공휴일
Date | Remarks
4310100% | 신정
4314600% | 설연휴
4314700% | 설연휴
4316000% | 삼일절
4322700% | 대체휴일
4324200% | 부처님오신날
4325700% | 현충일
4326400% | 지방선거
4332700% | 광복절
4336700% | 추석
4336800% | 추석
4336900% | 대체휴일
4337600% | 개천절
4338200% | 한글날
4345900% | 성탄절